## Summary
Braidwood Garden Club Event Planner: 2021-22
Meeting Date: | 2021-09-09 | Lead: | Charmian
What: | Flower Arranging Workshop led by Marilyn Carle (covid restrictions allowing)?
Where: | Braidwood Servicemens' Club
Meeting Date: | 2021-10-14 | Lead: | John
What: | Visit to Braidwood Gardens - Gabriele Borscz, Murray Harrex and David & Jennie Sutherland
Where: | Braidwood
Meeting Date: | 2021-11-11 | Lead: | Margy
What: | Visit to Local gardens Tarago
Where: | Tarago
Meeting Date: | 2021-12-09 | Lead: | John
What: | Christmas Party
Where: | Braidwood Servicemens' Club or Old Anglican Hall?
Meeting Date: | 2022-02-10 | Lead: | John
What: | Speaker: Stuart Read, Co-Chair, Australian Garden History Society
Where: | Braidwood Servicemens Club
Meeting Date: | 2022-03-10 | Lead: | Amanda
What: | Bus trip to Canberra public gardens
Where: | Canberra
Meeting Date: | 2022-04-14 | Lead: | Chris
What: | Visit to Local gardens in Reidsdale?
Where: | Reidsdale?
Meeting Date: | 2022-05-12 | Lead: | Bronwyn
What: | Visit to Noel and Trish Butler?
Where: | Morton?
Meeting Date: | 2022-06-09 | Lead: | ???
What: | Speaker / workshop
Where: | Braidwood Servicemens Club
Meeting Date: | 2022-07-14 | Lead: | Rose
What: | Visit to Dick and Virginia Groot-Obbink Truffle Farm
Where: | Durran Durra
Meeting Date: | 2022-08-11 | Lead: | John
What: | AGM and speaker
Where: | Mona?
Other ideas
What:
| Bus trip: National Arboretum and bonsai collection | Lead:
| Floriade 11/9-10/10 | Lead:
| Bus trip: Jennie and David Sutherland's coast home (Rosedale) | Lead:
| Bus trip to Kangaroo Valley | Lead: | Amanda
| Bus trip to Southern Highlands (eg Red Cow Farm, Sutton Forest) | Lead:
| Bus trip to Gunning and Taralga | Lead:
| Local gardens visits: David and Paula Grey (Elrington St - spring), Maria Wasson (Elrington St), Philip Hart (Duncan St - Spring), Kate Chinnick (Tudor Valley Road, Reidsdale - Spring), Kate & John Spring (Tudor Valley Road, Reidsdale - Spring), Fran McGrath (Hawthorn Lane), Richard Stone (Mongarlowe) | Lead:
| Local Garden visit to Araluen - Conrad & Jackie French | Lead:
| Local Garden visit to Majors Creek - Maureen Stachow (Wallaces Gap Rd - declined), Julie Hebbard (Long Flat) - September/October best. Other possible Majors Creek gardens are Judy Butcher, Sara Waters and Debbie Waters. | Lead: | Chris
| Tim Wimbone, Native Pepper Trees and other Mongarlowe gardens | Lead: | Charmian
| Visit Landtasia (Simone 0408 431 334 www.landtasiacompost.com/) for presentation on compost making and Malloon Institute (https://themullooninstitute.org) | Lead: | John / Jennie
| Talk topics: Rose cutting workshop | Lead: | Rose
| Talk topics: Tracey Bool | Lead: | Rose
| Talk topics: Beneficial insects (Jo McAuliffe?) | Lead: | Amanda
| Talk topics: Richard Stone | Lead: | Chris
| Talk topics: Stuart Read | Lead: | John
| Talk topics: Stephen Waring, Horticulturalist M: 0418 208 577. Topic: tbd | Lead: | John
| Talk topics: Dr Barry Conn on Prostantheron or Plants in PNG (cousin of Randal Lemin) | Lead:
| Talk topics: Wombats / attracting birds to gardens (George Storey?) | Lead: | Chris
| Talk topics: Sundials by Marg Folkard (Julia Bell's friend) | Lead:
| Talk topics: Garden design (Bec Bigg?) | Lead: | Chris
| Weekend trip: Orange, Millthorpe, Cowra | Lead:
| Talk topics: Native products - Noel Butler (Budawang Elder of the Yuin Nation - http://nuragunyu.com.au) from Bawley Point (Maria Bacas contact) or Fiona from Bent Shed (http://bentshedproduce.com.au) | Lead:
| Trip to Victoria | Lead:

## 9 Sep
Braidwood Garden Club meeting
Date: | 2021-09-09 | Lead: | Charmian
What: | Flower Arranging Workshop led by Marilyn Carle (covid restrictions allowing)?
Where: | Braidwood Servicemens' Club
Detail: | Awaiting Marilyn's proposal
Normally: | Morning tea: Members with surnames from A-L or provided?
Bring own cup, chair & lunch
| What | Status | Who to do
Organisation | Event confirmed with hosts | To do | Charmian
| Book Auditorium | To do | Jane
| Charge for event: | To do | Committee
| Booking sheet in Bendigo Bank - by 26/8 | To do | Amanda
| Blurb for newsletter / web page / social media | To do | Charmian
| Promoted in Garden Club Newsletter | To do | Margy
| Promoted on social media, Changing Times & Braidwood Radio | To do | Chris
| Promoted on Garden Club web page | To do | Fran
| Gifts for hosts organised | To do | John
| Raffle prizes and tickets organised | To do | Leonie
| Tea/coffee organised | To do | Charmian
| Re-confirm event with hosts (1 week before) | To do | Charmian
| Directions to venue | To do | Charmian
| Reminder email (1 week before event) | To do | Margy
| List of persons attending (including mobile number) | To do | Amanda
Follow-up: | Report drafted for Newsletter | To do | Charmian
| Thank you messages to hosts | To do | John
| Monies banked and reconciled | To do | Amanda
| Review outcome at Committee meeting | To do | Committee

## 14 Oct
Braidwood Garden Club meeting
Date: | 2021-10-14 | Lead: | John
What: | Visit to Braidwood Gardens - Gabriele Borscz, Murray Harrex and David & Jennie Sutherland
Where: | Braidwood
Detail: | David & Jennie Sutherland, 18 Coronation Drive |  | Yes
| Murray Harrex, 9 Bowler St, Braidwood |  | Yes
| Gabriele Borscz, "The Doncaster", Cnr Park Lane and Wilson St |  | Yes
Morning tea: Members with surnames from M-Z?
Bring own chair & lunch
| What | Status | Who to do
Organisation: | Event confirmed with hosts | Yes | John
| Blurb for newsletter / web page / social media | To do | John
| Promoted in Garden Club Newsletter | To do | Margy
| Promoted on social media, Changing Times & Braidwood Radio | To do | Chris
| Promoted on Garden Club web page | To do | Fran
| Gifts for hosts organised | To do | John
| Raffle prizes and tickets organised | To do | Leonie
| Tea/coffee organised | To do | Charmian
| Re-confirm event with hosts (1 week before) | To do | John
| Event reminder email | To do | Margy
Follow-up: | Report drafted for Newsletter | To do | Rose
| Thank you messages to hosts | To do | John
| Monies banked and reconciled | To do | Amanda
| Review outcome at Committee meeting | To do | Committee

## 11 Nov
Braidwood Garden Club meeting
Date: | 2021-11-11 | Lead: | Margy
What: | Visit to Local gardens Tarago
Where: | Tarago
Detail: | Bongalarby has agreed to us visiting them, Lyn Markeson is a possibility, and Margy is trying to persuade the owner of another property in Tarago. We can also add Nirvally nursery
Bring own cup, chair, morning tea & lunch, badge
| What | Status | Who to do
Organisation: | Event confirmed with hosts | To do | Margy
| Blurb for newsletter / web page / social media | To do | Margy
| Promoted in Garden Club Newsletter | To do | Margy
| Promoted on social media, Changing Times & Braidwood Radio | To do | Chris
| Promoted on Garden Club web page | To do | Fran
| Gifts for hosts organised | To do | John
| Raffle prizes and tickets organised | To do | Leonie
| Tea/coffee organised | To do | Charmian
| Re-confirm event with hosts (1 week before) | To do | Margy
| Event reminder email | To do | Margy
To do
Follow-up: | Report drafted for Newsletter | To do
| Thank you messages to hosts | To do | John
| Monies banked and reconciled | To do | Leonie / Amanda
| Review outcome at Committee meeting | To do | Committee

## 9 Dec
Braidwood Garden Club meeting
Date: | 2021-12-09 | Lead: | John
What: | Christmas Party
Where: | Braidwood Servicemens' Club or Old Anglican Hall?
Detail: | Venue - Old Anglican Hall if finished in time |  | Chris
| Servicemen's Club Auditorium booked in reserved |  | Amanda
Alison Stuchberry (Sweet Creation): unfortunately no.
Contact Vanessa
Quiz by Rose and Bronwyn
Champagne provided by BGC?
| What | Status | Who to do
Organisation: | Venue booked | Yes
| Catering booked | To do | John
| Cost of event | To do | Committee
| Booking sheet in Bendigo Bank - by 27/11 | To do | Amanda
| Basic blurb for newsletter / web page / social media | To do | John
| Promoted in Garden Club Newsletter | To do | Margy
| Promoted on social media, Changing Times & Braidwood Radio | To do | Chris
| Promoted on Garden Club web page | To do | Fran
| Raffle prizes, lucky door prize and tickets organised | To do | Leonie
| Nibbles made - will coordinate what in November | To do | Committee
| Re-confirm event with hosts (1 week before) | To do | John
| Quiz questions | To do | Rosemary / Bronwyn
| Guess the plant - pictures or foliage | To do | Rosemary / Bronwyn
| Plant swap / gold coin donation | To do | Jennie
| Catering confirmed (4 weeks before) | Done | John
| Event reminder email | To do | Margy
| List of persons attending | To do | Amanda
To do
Follow-up: | Report drafted for Newsletter | To do | John
| Monies banked and reconciled | To do | Leonie / Amanda
| Review outcome at Committee meeting | To do | Committee

## 10 Feb
Braidwood Garden Club meeting
Date: | 2022-02-10 | Lead: | John
What: | Speaker: Stuart Read, Co-Chair, Australian Garden History Society
Where: | Braidwood Servicemens Club
Detail: | Topic:
A history of garden design using Australian native plants (1788-now)
Ten Lessons from Historic Gardens
No car. Lives in Sydney and can borrow Catherine Tuckwell's car. BGC needs to pay petrol. Staying at the Tuckwell's.
Looking into making it a work trip by giving a talk to the BCA wearing his Heritage NSW hat.
Morning tea: Biscuits. Members with surnames from M-Z bring morning tea
| What | Status: | Who to do
Organisation: | Event confirmed with speaker | Done | John
| Room booked for meeting | To do | Jane
| Cost of event? - free | To do | Committee
| Blurb for newsletter / web page / social media | To do | John
| Promoted in Garden Club Newsletter | To do | Margy
| Promoted on social media, Changing Times & Braidwood Radio | To do | Chris
| Promoted on Garden Club web page | To do | Fran
| Gifts for speaker organised | To do | John
| Raffle prizes and tickets organised | To do | Leonie
| Tea/coffee organised | To do | Charmian
| Re-confirm event with hosts (1 week before) | To do | John
| Reminder email (1 week before event) | To do | Margy
Follow-up: | Report drafted for Newsletter | To do | John
| Thank you messages to hosts | To do | John
| Monies banked and reconciled | To do | Leonie / Amanda
| Review outcome at Committee meeting | To do | Committee

## 10 Mar
Braidwood Garden Club meeting
Date: | 2022-03-10 | Lead: | Amanda
What: | Bus trip to Canberra public gardens
Where: | Canberra
Detail: | National Botenical Gardens
National Botanical Arboretum and bonsai collection
Old Parliamnet House Rose Gardens
Morning tea: Members with surnames from A-L
Bring own cup, chair & lunch
| What | Status | Who to do
Organisation | Event confirmed with hosts | To do | Amanda
| Charge for event: | To do | Committee
| Blurb for newsletter / web page / social media | To do | Amanda
| Promoted in Garden Club Newsletter | To do | Margy
| Promoted on social media, Changing Times & Braidwood Radio | To do | Chris
| Promoted on Garden Club web page | To do | Fran
| Gifts for hosts organised | To do | John
| Raffle prizes and tickets organised | To do | Leonie
| Tea/coffee organised | To do | Charmian
| Re-confirm event with hosts (1 week before) | To do | Amanda
| Directions to venue | To do | Amanda
| Reminder email (1 week before event) | To do | Margy
| List of persons attending (including mobile number) | To do | Amanda
Follow-up: | Report drafted for Newsletter | To do | Amanda
| Thank you messages to hosts | To do | John
| Monies banked and reconciled | To do | Leonie / Amanda
| Review outcome at Committee meeting | To do | Committee

## 14 Apr
Braidwood Garden Club meeting
Date: | 2022-04-14 | Lead: | Chris
What: | Visit to Local gardens in Reidsdale?
Where: | Reidsdale?
Detail: | Peter Marshall
Kate Chinnick (Tudor Valley Road)
Kate & John Spring (Tudor Valley Road)
Bring own cup, chair & lunch?
| What | Status | Who to do
Organisation: | Event confirmed with hosts | To do | Chris
| Blurb for newsletter / web page / social media | To do | Chris
| Promoted in Garden Club Newsletter | To do | Margy
| Promoted on social media, Changing Times & Braidwood Radio | To do | Chris
| Promoted on Garden Club web page | To do | Fran
| Gifts for hosts organised | To do | John
| Raffle prizes and tickets organised | To do | Leonie
| Tea/coffee organised | To do | Charmian
| Re-confirm event with hosts (1 week before) | To do | Chris
| Bus confirmed (1 week before) | To do | Chris
| Directions to venue | To do | Chris
| Reminder email (1 week before event) | To do | Margy
| List of persons attending | To do | Amanda
Follow-up: | Report drafted for Newsletter | To do | Chris
| Thank you messages to hosts | To do | John
| Monies banked and reconciled | To do | Leonie / Amanda
| Review outcome at Committee meeting | To do | Committee

## 12 May
Braidwood Garden Club meeting
Date: | 2022-05-12 | Lead: | Bronwyn
What: | Visit to Noel and Trish Butler?
Where: | Morton?
Detail: | Talk topics: Native products - Uncle Noel and Trish Butler (Budawang Elders of the Yuin Nation - http://nuragunyu.com.au M:0405 646 911 E: nuragunyu@gmail.com)
Conversational presentation including: welcome to country, local history, food, native plants and edible plants including growing them, and the environment.
Charge is $20.
Address: 501 Wheelbarrow Rd, MORTON NSW 2538
Barry and Christine Matthews (O414 900 187 E: invspice@gmail.com)
24 Hobbs Lane, Woodstock
Lunch, talk on talks on propagating natives from seed and propagating kangaroo paws and visit to their native garden.
Lunch: BYO and chair
Bring own cup, chair & lunch
| What | Status | Who to do
Organisation: | Event confirmed with hosts | To do | Bronwyn
| Cost of bus - $1200? | To do | Jane
| Cost of workshop - $20? | To do | Bronwyn
| Blurb for newsletter / web page / social media | To do | Bronwyn
| Promoted in Garden Club Newsletter | To do | Margy
| Promoted on social media, Changing Times & Braidwood Radio | To do | Chris
| Included in Braidwood Times ‘What’s on’ notices | To do | Jennie
| Promoted on Garden Club web page | To do | Fran
| Gifts for hosts organised | To do | John
| Raffle prizes and tickets organised | To do | Leonie
| Tea/coffee organised | To do | Charmian
| Re-confirm event with hosts (1 week before) | To do | Bronwyn
| Directions to venue | To do | Bronwyn
| Reminder email (1 week before event) | To do | Margy
Follow-up: | Report drafted for Newsletter | To do | Bronwyn
| Thank you messages to hosts | To do | John
| Monies banked and reconciled | To do | Leonie / Amanda
| Review outcome at Committee meeting | To do | Committee

## 9 Jun
Braidwood Garden Club meeting
Date: | 2022-06-09 | Lead: | ???
What: | Speaker / workshop
Where: | Braidwood Servicemens Club
Detail: | Talk topics: Tracey Bool |  | Rose
| Talk topics: Beneficial insects (Jo McAuliffe?) |  | Amanda
| What | Status: | Who to do
Organisation: | Event confirmed with hosts | To do | ???
| Blurb for newsletter / web page / social media | To do | ???
| Promoted in Garden Club Newsletter | To do | Margy
| Promoted on social media, Changing Times & Braidwood Radio | To do | Chris
| Promoted on Garden Club web page | To do | Fran
| Gifts for hosts organised | To do | John
| Raffle prizes and tickets organised | To do | Leonie
| Tea/coffee organised | To do | Charmian
| Re-confirm event with hosts (1 week before) | To do | ???
| Reminder email (1 week before event) | To do | Margy
Follow-up: | Report drafted for Newsletter | To do | ???
| Thank you messages to hosts | To do | John
| Monies banked and reconciled | To do | Leonie / Amanda
| Review outcome at Committee meeting | To do | Committee

## 14 Jul
Braidwood Garden Club meeting
Date: | 2022-07-14 | Lead: | Rose
What: | Visit to Dick and Virginia Groot-Obbink Truffle Farm
Where: | Durran Durra
Detail: | 45 Brightside Rd, Durran Durra
T: 4842 1792 E: lengrow@bigpond.com
Lunch: Members with surnames from A-L?
| What | Status: | Who to do
Organisation: | Event confirmed with hosts | To do | Rose
| Cost of workshop - ? | To do | Rose
| Booking sheet in Bendigo Bank | To do | Amanda
| Blurb for newsletter / web page / social media | To do | Rose
| Promoted in Garden Club Newsletter | To do | Margy
| Promoted on social media, Changing Times & Braidwood Radio | Done | Chris
| Promoted on Garden Club web page | To do | Fran
| Gifts for hosts organised | To do | John
| Raffle prizes and tickets organised | To do | Leonie
| Tea/coffee organised | To do | Charmian
| Re-confirm event with hosts (1 week before) | To do | Rose
| Reminder email (1 week before event) | To do | Margy
Follow-up: | Report drafted for Newsletter | To do | Rose
| Thank you messages to hosts | To do | John
| Monies banked and reconciled | To do | Leonie / Amanda
| Review outcome at Committee meeting | To do | Committee

## 11 Aug
Braidwood Garden Club meeting
Date: | 2022-08-11 | Lead: | John
What: | AGM and speaker
Where: | Mona?
Detail: | Talk topics: Tracey Bool |  | Rose
| Talk topics: Beneficial insects (Jo McAuliffe?) |  | Amanda
| What | Status: | Who to do
Organisation: | Event confirmed with speaker | To do | Rose
| Room booked for meeting | To do | John
| Charge for event | To do | Committee
| Booking sheet in Bendigo Bank | To do | Amanda
| Blurb for newsletter / web page / social media | To do | Rose
| Promoted in Garden Club Newsletter | To do | Margy
| Promoted on social media, Changing Times & Braidwood Radio | To do | Chris
| Promoted on Garden Club web page | To do | Fran
| Gifts for hosts organised | To do | John
| Raffle prizes and tickets organised | To do | Leonie
| Tea/coffee organised | To do | Charmian
| Re-confirm event with hosts (1 week before) | To do | John
| Reminder email (1 week before event) | To do | Margy
To do
Follow-up: | Report drafted for Newsletter | To do | John
| Thank you messages to hosts | To do | John
| Monies banked and reconciled | To do | Leonie / Amanda
| Review outcome at Committee meeting | To do | Committee